## Start Here
TapeAndFloat 2-Week Lookahead: Subs & Inspections Schedule (free)
For small home builders, GCs and remodelers who schedule by text. One sheet that shows who is on which job, and which inspections are coming up.
1. Schedule sheet: one row per job per task. Job / address, task (e.g. Frame walls, Rough plumbing, Drywall hang), Type (Sub work, Inspection, Delivery, Other),
the sub or crew and their phone, start and end dates. For an inspection row, the start date is the day you need the inspection.
2. When the sub confirms (a text back is enough), set Confirmed to Y. Confirm by is worked out for you: start date minus the days on Settings.
3. Depends on: the task name (same job) that must finish first, e.g. 'Rough-in inspection' before 'Insulation'. The sheet flags a start before that task ends.
4. Inspections: set Requested to Y once you have asked for it, add the inspection date, then the result (Pass, Fail, Partial) and any re-inspection date.
5. Lookahead column: Now, Week 1, Week 2 or Later, so you can filter to the next two weeks and send each sub their dates.
Red = start coming up and not confirmed, failed or partial inspection with no re-inspection date, or the same sub on two jobs on the same day.
Yellow = inspection not requested yet, no sub assigned, starts before the task it depends on ends, or no start date. Green = confirmed or passed.
Tip: review the next two weeks at the same time each day, and text each sub the dates for their rows. Your inspection office sets its own
request rules and lead times; put your lead time on Settings.
Guide: https://gc.tapeandfloat.com/guides/scheduling-subs-inspections-lookahead.html
Want this kept up for you? During the TapeAndFloat pilot we set up, one piece at a time, a list of who is on which job plus inspection reminders
from the texts and emails you forward, in your own Google Sheet. You approve before anything goes out, and a real person reviews everything.
Free 60-day pilot, no card: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Summary (updates automatically)
Rows in the lookahead window (Now, Week 1, Week 2)
Starting soon and not confirmed
Inspections not requested yet
Failed or partial inspections with no re-inspection date
Rows with a sub on two jobs at the same time
Rows with no sub assigned
Rows starting before the task they depend on ends
Rows with any flag
Free to use and share. No warranty; general information, not legal advice. Check your local inspection office's own rules.

## Schedule
Job / address | Task | Type | Sub / crew (or inspector) | Phone | Start (date) | End (date) | Confirmed? (Y/N) | Confirm by (date) | Depends on (task, same job) | Inspection requested? (Y/N) | Inspection date | Inspection result | Re-inspection date | Days until start | Lookahead | Flag | Notes | End used (helper)

## Settings
Settings
Confirm subs this many days before their start date | 2
Request inspections this many days before the inspection date (use your office's lead time) | 2
Lookahead window in days (Week 1 = first 7 days, Week 2 = the rest) | 14
Edit the values in column B. These are your own settings, not an industry or code rule.