## Start Here
TapeAndFloat Allowance & Client Selections Tracker (free)
For small home builders and remodelers. One row per allowance in the contract (tile, fixtures, lighting, cabinets, countertops, appliances...).
1. From the contract: job, category, allowance amount, and whether the allowance is material only or installed.
2. Selection due date: when the client must pick to keep the schedule (when the trade needs it on site, minus supplier lead time).
3. When the client picks: enter the date, the supplier quote or invoice number, and the actual cost on the SAME basis as the allowance.
Difference = actual cost minus allowance. If it is over, the change order amount adds your markup % (cell B22 below, editable per row).
4. Overages: enter the change order number and the date the client signed it BEFORE you order. Then the date or draw it was billed on.
Credits (picked under the allowance): enter the date or invoice it was credited on to close the row.
Red = selection past due, or over the allowance with no signed change order.
Yellow = selection due within 14 days, signed overage not billed yet, or credit not applied yet.
Green = closed (billed, credited, or on budget).
Tip: send the client the full list of selection dates at the start of the job, and again two weeks before each one.
Guide: https://gc.tapeandfloat.com/guides/allowance-selections-tracking.html
Want this kept up for you? TapeAndFloat reads the client texts, showroom emails and supplier quotes you forward,
updates each allowance row in your own Google Sheet, and lists upcoming selection dates and unbilled overages every morning.
Free 60-day pilot, no card: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Default markup % on overages: | 15%
Free to use and share. No warranty. Follow your own contract's allowance and change order terms.

## Allowances
Job / client | Category | Item / description | Allowance $ | Basis (Material / Installed) | Selection due | Selected on (date) | Supplier quote / invoice # | Actual cost $ (same basis) | Difference $ | Markup % (blank = default) | Change order $ | CO # | CO signed (date) | Billed / credited on (date or draw #) | Status | Flag | Notes