## Start Here
TapeAndFloat Daily Log & Job Photo Tracker (free)
For small builders, remodelers and GCs. One row per job per day: who was on site, the weather, the work done, deliveries, inspections, visitors,
delays and their cause, instructions or changes the client gave, safety notes and a link to that day's photo folder.
1. Jobs sheet: one row per job (up to 20 are checked for missing logs). Start date, end date (blank = still going) and status (Active, On hold, Done).
2. Daily Log sheet: one row per job per workday, written the same day. Keep it factual: what happened, who was there, what was said, by whom.
If the client asks for a change, write it down and mark whether it became a written change order (Yes / No / Not needed).
Paste the link to the job's photo folder for that day (for example a shared folder named Job / 2026-10-26).
3. Missing Logs sheet: every workday in your lookback window, for every active job, marked MISSING when there is no log row.
4. Settings: which weekdays are workdays, days off you don't want flagged (holidays, shutdowns), how far back to check, and when a log counts as written late.
Red = client instruction not turned into a change order, or a delay with no cause written down.
Yellow = no photos link, crew count blank, inspection with no result, no work written, job not on the Jobs sheet, two rows for the same job and day, written late.
Green = complete row.
5. The first rows are EXAMPLES (the job name starts with EXAMPLE). Delete them, on Jobs and Daily Log, before you start.
Photo habits: date every photo, label it by job and room or area, take a wide shot and a close shot, shoot walls before they are covered
(before drywall), during and after, and keep the originals in one folder per job by date.
A good daily log may help if there is ever a dispute. It is a record, not legal advice; ask an attorney about your situation.
Guide: https://gc.tapeandfloat.com/guides/daily-logs-job-photos.html
Want help keeping it up? During the TapeAndFloat pilot, photos texted from the field are filed on the job by date and missing daily logs get flagged.
You approve anything that goes out, and a real person reviews everything.
Free 60-day pilot: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Summary (updates automatically)
Active jobs
Workdays with no log (active jobs, lookback window)
Log rows
Rows with no photos link
Delays with no cause
Client instructions not turned into a change order
Inspections with no result
Rows with crew count blank
Rows written late
Rows with any flag
Free to use and share. No warranty; general information only, not legal advice.

## Daily Log
Date | Job | Our crew on site (count) | Subs on site (companies) | Sub crew count | Weather | Work done today | Deliveries | Inspection (type) | Inspection result | Visitors (client, inspector, others) | Delay today? | Delay cause | Client instructions / changes given | Turned into a change order? | Safety notes | Photos folder link | Logged by | Written on (date) | Flag | Notes
2026-10-25 | EXAMPLE Smith kitchen (delete this row) | 3 | ABC Electric | 2 | Sunny, 80s | Framing punch, electrical rough-in kitchen | Cabinets delivered (checked vs order) | Electrical rough | Pass | Inspector; owner walked site | No |  | Owner asked to move island outlet 12 in. left | Yes | None | https://drive.example.com/smith/2026-10-26 | Ana | 2026-10-26 |  | Example: complete row
2026-10-24 | EXAMPLE Smith kitchen (delete this row) | 3 |  |  | Rain AM | Interior blocking only |  |  |  |  | Yes |  |  |  | Wet floor at back door, mat put down |  | Ana | 2026-10-24 |  | Example: delay with no cause, no photos link
2026-10-23 | EXAMPLE Smith kitchen (delete this row) |  | Pro Plumbing | 3 | Cloudy | Plumbing top-out |  | Plumbing top-out |  | Owner | No |  | Owner wants a second vanity light | No |  | https://drive.example.com/smith/2026-10-23 | Ana | 2026-10-25 |  | Example: client change with no change order, inspection with no result, crew count blank, written late
2026-10-21 | EXAMPLE Lee addition (delete this row) | 2 |  |  | Sunny | Foundation forms | Rebar |  |  |  | No |  |  |  |  | https://drive.example.com/lee/2026-10-21 | Ben | 2026-10-21 |  | Example: Lee job has workdays with no log since

## Jobs
Job | Address | Start date | End date (blank = still going) | Status | Workdays with no log (lookback) | Last log date | Flag | Notes
EXAMPLE Smith kitchen (delete this row) | Oak St | 2026-09-26 |  | Active
EXAMPLE Lee addition (delete this row) | Pine Rd | 2026-10-06 |  | Active
EXAMPLE Diaz bath (delete this row) | Elm Ave | 2026-08-27 | 2026-10-01 | Done

## Missing Logs
Date | Workday?

## Settings
Settings | Workday? (Yes / No) | Days off not to flag (holidays, shutdowns)
Monday | Yes
Tuesday | Yes
Wednesday | Yes
Thursday | Yes
Friday | Yes
Saturday | No
Sunday | No
Lookback: check this many days back for missing logs (max 60) | 14
Flag a log written more than this many days after the work day | 1
Edit the yellow cells. These are your own settings, not a rule.