## Start Here
TapeAndFloat Delay Log (free)
For small builders, remodelers and GCs. One row per delay: weather, a homeowner decision or selection, a material backorder, an inspection,
a sub who didn't show, a change order or anything else that pushes the schedule. Write it down the day it starts and tell the client in writing.
1. Jobs sheet: one row per job (client and address). The Delay Log checks that each job name matches this list.
2. Delay Log sheet: one row per delay. Date started, cause, a short factual description, estimated days lost and who caused it or owns the fix.
Then: was the client notified, on what date and how (email, text, letter or app are written; a phone call or in-person talk is not, so follow it up in writing),
did the client confirm in writing (needed for their own decisions and selections), was the schedule updated, does it need a change order (and its number),
the cost impact if any, and a link to the photos or daily log. Leave the end date blank while the delay is still open.
3. Settings: how many days after a delay starts you want the client notified, and how long a delay can stay open before it is flagged.
The numbers there are EXAMPLES, not rules. Notice periods and any right to more time are set by your contract; ask an attorney about your situation.
Red = no written notice to the client, a client decision with no written OK, or a change order needed with no change order number.
Yellow = notice later than your Settings, backorder with no new delivery date, days lost blank, job not on the Jobs sheet, open with no end date, no cause or no start date.
Green = complete row.
4. The first rows are EXAMPLES (the job name starts with EXAMPLE). Delete them, on Jobs and Delay Log, before you start.
Keep it factual: what happened, when, who was told, and what they said. Leave out blame. A clear record may help if there is ever a dispute;
it is general information, not legal advice.
Guide: https://gc.tapeandfloat.com/guides/documenting-construction-delays.html
Want help keeping it up? During the TapeAndFloat pilot, a delay with no written notice to the client gets flagged and a short update is drafted
for your office to approve. We set it up one piece at a time, and a real person reviews everything.
Free 60-day pilot: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Summary (updates automatically)
Delays logged
Open delays (no end date)
Days lost (estimated, total)
Cost impact (total)
Delays with no written notice to the client
Notice later than your Settings
Client decisions with no written OK
Backorders with no new delivery date
Change order needed, no change order number
Days lost blank
Job not on the Jobs sheet
Open past your Settings with no end date
Rows with any flag
Free to use and share. No warranty; general information only, not legal advice.

## Delay Log
Job | Date started | Date ended (blank = open) | Cause | What happened (facts only) | Days lost (est.) | Who caused it / owns the fix | Client notified? | Date client notified | How notified | Client written OK / acknowledgment? | Schedule updated? | New delivery date (backorders) | Change order needed? | Change order # | Cost impact ($) | Photos / daily log link | Flag | Notes
EXAMPLE Smith kitchen (delete this row) | 2026-10-06 | 2026-10-08 | Weather | Rain two days; no exterior work | 2 | Weather | Yes | 2026-10-07 | Email | Not needed | Yes |  | No |  |  | https://drive.example.com/smith/log |  | Example: complete row
EXAMPLE Smith kitchen (delete this row) | 2026-10-14 |  | Homeowner decision / selection | Waiting on owner's tile choice for the shower; tile setter rescheduled | 4 | Owner | Yes | 2026-10-15 | Phone call | No | Yes |  | Yes |  |  |  |  | Example: notified by phone only, no written OK, CO needed with no number, still open
EXAMPLE Lee addition (delete this row) | 2026-10-20 |  | Material backorder | Windows backordered at supplier |  | Supplier | Yes | 2026-10-25 | Email |  | No |  | No |  |  |  |  | Example: notice late, no new delivery date, days lost blank
EXAMPLE Lee addition (delete this row) | 2026-10-23 | 2026-10-24 | Inspection | Framing inspection failed; re-inspection booked | 1 | Us (blocking missing) | No |  |  |  | Yes |  | No |  | 150 | https://drive.example.com/lee/log |  | Example: client not notified

## Jobs
Job | Client | Address | Status | Delays | Open delays | Days lost (est.) | Cost impact | Rows with a flag | Notes
EXAMPLE Smith kitchen (delete this row) | Smith | Oak St | Active
EXAMPLE Lee addition (delete this row) | Lee | Pine Rd | Active

## Settings
Settings
Notify the client in writing within this many days of the delay starting (EXAMPLE value; check your contract) | 2
Flag a delay still open (no end date) after this many days (EXAMPLE value) | 7
Edit the yellow cells. These are your own settings, not a rule. Notice periods and delay or extension rights are set by your contract; ask an attorney.