## Start Here
TapeAndFloat drywall change order log (free Excel workbook)
Yellow cells are for you to type in. White cells are formulas: they calculate on their own. The sheet is not locked, so you can change anything.
Rows that start with EXAMPLE are sample data, not real jobs and not prices. Delete them (or type over them) before you use the sheet.
1. Change Order Log sheet: one row per change order, added the day the change is requested. Type the job, CO number, date sent, a short description and who asked for it.
2. Price it one of two ways: type a lump sum (or the T&M total from signed tickets) in "Lump sum / T&M total", or type the quantity and your unit price.
CO amount = lump sum / T&M total if you typed one, otherwise quantity x your unit price. Use your own prices.
3. Pick a status from the list: Pending (sent, not approved yet), Approved, Rejected or Billed.
When it is approved, type who approved it, the approval date and the proof (signed form, email). When you bill it, change the status to Billed and type the invoice or pay app number.
4. Type the date the crew started the changed work, so the sheet can tell you if work started before the approval date.
5. Days pending counts from the date sent to today (TODAY()) while the status is Pending.
6. The Check column flags QTY OR PRICE MISSING, NO STATUS, APPROVED - NO APPROVAL DATE OR PROOF, WORK STARTED BEFORE APPROVAL,
PENDING OVER 7 DAYS, PENDING - NO DATE SENT, APPROVED - NOT BILLED YET and BILLED - NO INVOICE #. Rows with a flag turn orange;
rows pending over 7 days or with work started before approval turn red.
7. Under the table: count and amount by status, the approved amount not billed yet, and billed change orders not paid yet.
Review the log once a week: chase signatures on old pending rows and put approved rows on the next invoice or pay app.
How-to guide, change order form (PDF) and the CSV version: https://tapeandfloat.com/guides/change-order-template.html
Spanish version: TapeAndFloat_Registro_Ordenes_de_Cambio_Drywall.xlsx (https://tapeandfloat.com/es/plantilla-orden-de-cambio-drywall.html)
Want help catching extras before they slip? TapeAndFloat is an AI office assistant that reads the texts and emails you forward and flags
change orders with no written approval and approved extras that never made it onto an invoice, in a Google Sheet. Free 60-day pilot: https://tapeandfloat.com/office-assistant.html Questions: james@tapeandfloat.com
Free to use and share. No warranty; general information, not legal, tax or accounting advice. What counts as an approved change order depends on your subcontract.

## Change Order Log
Drywall change order log
Yellow = you type. White = formulas. EXAMPLE rows are sample data, not prices: delete them before you use the sheet.
Today (days pending count to this date):
Job | CO # | Date sent | Description of change | Requested by | Pricing method | Qty | Unit | Your unit price $ | Lump sum / T&M total $ | CO amount $ | Status | Approved by | Approval date | Approval proof (signed form, email) | Work started | Billed on (invoice / pay app #) | Paid date | Days pending | Check | Notes
EXAMPLE – Lot 14 (delete this row) | CO-001 | 2026-10-02 | Add garage walls and ceiling, Level 4 | Site super | Lump sum |  |  |  | 1000 |  | Approved | [GC PM name] | 2026-10-05 | Signed form | 2026-10-07 |  |  |  |  | Sample: placeholder amount, not a price
EXAMPLE – Unit 3 (delete this row) | CO-002 | 2026-10-12 | Patch walls after plumber rework | GC PM | T&M |  |  |  | 500 |  | Pending |  |  |  | 2026-10-13 |  |  |  |  | Sample: signed T&M tickets, still waiting on the CO
EXAMPLE – Lot 9 (delete this row) | CO-003 | 2026-09-15 | Upgrade great room to Level 5 | Homeowner via GC | Unit price | 100 | sq ft | 10 |  |  | Billed | [GC PM name] | 2026-09-18 | Email | 2026-09-22 | INV-1004 | 2026-10-20 |  |  | Sample: placeholder numbers, not prices
EXAMPLE – Lot 2 (delete this row) | CO-004 | 2026-10-26 | Add soffit over kitchen cabinets | Site super | Unit price | 20 | lin ft |  |  |  | Pending | [8 empty] | Sample: unit price not typed yet
EXAMPLE – Lot 7 (delete this row) | CO-005 | 2026-10-08 | Moisture-resistant board in laundry | GC PM | Lump sum |  |  |  | 300 |  | Approved | [8 empty] | Sample: verbal OK only, get it in writing
EXAMPLE – Unit 5 (delete this row) | CO-006 | 2026-10-01 | Rehang wall moved by framer | Site super | Lump sum |  |  |  | 800 |  | Rejected | [GC PM name] |  | Email | [5 empty] | Sample: GC says it was in the base scope
TOTAL (all change orders)
CHANGE ORDERS BY STATUS
Status | [8 empty] | Count | Amount $
Pending
Approved
Rejected
Billed
Approved, not billed yet (put these on the next invoice or pay app)
Billed, no paid date yet
Pending over 7 days (count)
Rows with a flag (count)
Formulas:
Days pending = IF(NOT(OR([Job]<>"",[CO #]<>"",[Description of change]<>"")),"",IF(AND([Status]="Pending",[Date sent]<>""),MAX(0,TODAY()-[Date sent]),""))