## Start Here
TapeAndFloat drywall delivery / receiving checklist (free Excel workbook)
A receiving checklist is what the foreman or office fills in when material lands on the job: what was ordered, what actually arrived, what came damaged, wet or wrong, and where it was stocked.
This workbook keeps it as a log with one row per item per delivery. Yellow cells are for you to type in. White cells are formulas: they calculate on their own.
The sheet is not locked, so you can change anything. Rows that start with EXAMPLE are sample data, not real jobs or deliveries. Delete them (or type over them) before you use the sheet.
1. Receiving Log sheet: one row per item per delivery. Type the job, the deliver-to address, the supplier and the PO or delivery ticket #.
Use the same PO # as on your material order so the two match up.
2. Type the scheduled delivery date when you place the order. When the load arrives, type the actual delivery date.
3. Pick the material from the list (Board, Mud / compound, Tape, Corner bead / trim, Screws / fasteners, Adhesive, Primer, Texture, Sanding, Other),
then type the size / type (1/2" regular, 5/8" Type X, moisture-resistant...), the unit, the qty ordered and the qty received.
4. Count before the driver leaves, if you can. Type how many came damaged, wet or wrong, where it was stocked (floor and rooms) and who checked it.
Type Y in Signed delivery ticket once the ticket is signed (with any shortage or damage noted on it), and paste a photo link (Google Drive, Dropbox or your photo app).
5. Short (-) / over (+) = qty received - qty ordered. A minus number means the load came short.
Days until scheduled delivery counts from today (TODAY()) to the scheduled date. A minus number means it is late. It goes blank once the material is received.
Days since received counts from the actual delivery date to today.
6. The Check column flags NO JOB, NO PO #, SHORT SHIPPED, OVER SHIPPED, DAMAGED - NO PHOTO (a damaged qty with no photo link),
NOT SIGNED (received, but Signed delivery ticket is not Y) and DELIVERY DATE PASSED - NOT RECEIVED.
Short-shipped rows, damaged rows with no photo and late deliveries turn red; other flagged rows turn orange.
7. Under the table: a summary of lines, received, still waiting, due in the next 7 days, short and over shipped (lines and qty), damaged qty,
damaged with no photo, not signed, late deliveries and flagged rows. Check it the day of each delivery, before you call or email the supplier.
How-to guide, a bilingual text format for the foreman, a supplier email and the CSV version: https://tapeandfloat.com/templates/drywall-delivery-receiving-checklist.html
Spanish version: TapeAndFloat_Lista_Recepcion_Materiales_Drywall.xlsx (https://tapeandfloat.com/es/plantillas/plantilla-lista-recepcion-materiales-drywall.html)
Report short, damaged or wrong material to the office and the supplier the same day. TapeAndFloat is an AI office assistant that reads the texts and emails
you forward and keeps jobs, crews and money straight in a Google Sheet. Free 60-day pilot: https://tapeandfloat.com/office-assistant.html Questions: james@tapeandfloat.com
Free to use and share. No warranty; general information, not legal, contract, tax or accounting advice. Check your supplier terms for how to report shortages and damage.

## Receiving Log
Drywall delivery / receiving checklist
Yellow = you type. White = formulas. EXAMPLE rows are sample data: delete them before you use the sheet.
Today (days until and days since count from this date):
Job | Deliver-to address | Supplier | PO / delivery ticket # | Scheduled delivery date | Actual delivery date | Material | Size / type | Unit | Qty ordered | Qty received | Short (-) / over (+) | Damaged / wet / wrong qty | Stocked where / floor | Received / checked by | Signed delivery ticket? (Y/N) | Photo link | Days until scheduled delivery (minus = late) | Days since received | Check | Notes
EXAMPLE Lot 14 (delete this row) | [job address] | [supplier] | [PO #] |  |  | Board | 5/8" Type X, [length] | sheets | 60 | 56 |  | 3 | 2nd floor, bedrooms | Crew 1 (Marco) | Y | [photo link] |  |  |  | Sample: 4 short, 3 broken corners
EXAMPLE Lot 14 (delete this row) | [job address] | [supplier] | [PO #] |  |  | Mud / compound | All-purpose, [size] | boxes | 40 | 40 |  | 0 | Garage | Crew 1 (Marco) | Y |  |  |  |  | Sample: no flag
EXAMPLE Lot 14 (delete this row) | [job address] | [supplier] | [PO #] |  |  | Corner bead / trim | [type and length] | pieces | 50 | 50 |  | 4 | Garage | Crew 1 (Marco) | N |  |  |  |  | Sample: bent pieces, no photo, ticket not signed
EXAMPLE Lot 7 (delete this row) | [job address] | [supplier] | [PO #] |  |  | Board | 1/2" regular, [length] | sheets | 80 | [10 empty] | Sample: late, call the supplier
EXAMPLE Lot 7 (delete this row) | [job address] | [supplier] | [PO #] |  |  | Screws / fasteners | [size] | boxes | 10 | [10 empty] | Sample: not due yet, no flag
EXAMPLE Lot 7 (delete this row) | [job address] | [supplier] |  |  |  | Tape | Paper, [roll length] | rolls | 20 | 24 |  | 0 | 1st floor | Crew 3 (Ana) | Y |  |  |  |  | Sample: 4 extra rolls, no PO # typed
SUMMARY
Count
Lines (rows in use)
Received (actual date or qty received typed)
Still waiting (not received yet)
Due in the next 7 days (not received)
Delivery date passed - not received (call the supplier)
Short shipped (lines)
Short shipped (total qty missing)
Over shipped (lines)
Damaged / wet / wrong (total qty)
Damaged - no photo (take the photo)
Received - delivery ticket not signed
Rows with a flag (count)
Formulas:
Days since received = IF(NOT(OR([Job]<>"",[Deliver-to address]<>"",[Supplier]<>"",[PO / delivery ticket #]<>"",[Scheduled delivery date]<>"",[Actual delivery date]<>"",[Material]<>"",[Size / type]<>"",[Qty ordered]<>"",[Qty received]<>"",[Damaged / wet / wrong qty]<>"")),"",IF(ISNUMBER([Actual delivery date]),TODAY()-[Actual delivery date],""))