## Start Here
TapeAndFloat Job Budget vs Actual Tracker (free)
For small home builders, GCs and remodelers. See budget vs actual for every job and cost code without accounting software.
1. Budget sheet: one row per job and cost code (use the same short cost code list on every job). Enter the original budget from your estimate.
2. Costs sheet: one row per bill, sub invoice, receipt or labor entry, with the job, cost code and amount. Do it the week it comes in.
Job and cost code must match the Budget sheet exactly. Enter credits and returns as negative amounts.
3. Change Orders sheet: one row per change order. Signed change orders are added to that line's budget automatically (revised budget).
Enter the date or invoice # you billed it, so signed change orders never go unbilled.
4. The Budget sheet works out actual cost to date, variance $ (revised budget minus actual; negative = over) and variance % of the revised budget.
Red = over budget, or costs on a line with no budget. Yellow = near budget (share set on Settings) while the work is not done,
costs with no job, no cost code or no matching budget line, change orders worked but not signed, or signed but not billed.
Green = work done and within budget.
Tip: review the short list every week. Over budget = find out why and whether a change order is owed.
Guide: https://gc.tapeandfloat.com/guides/job-cost-tracking-budget-vs-actual.html
Want this kept up for you? Forward receipts and bills; TapeAndFloat codes them to the job and cost code in your own Google Sheet
and flags overruns and unbilled change orders weekly. You approve; nothing is paid or sent without you.
Free 60-day pilot, no card: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Summary (updates automatically)
Budget lines over budget
Budget lines near budget (work not done)
Total over budget ($)
Costs with no job
Costs with no cost code
Costs with no matching budget line
Change orders worked but not signed
Signed change orders not billed (count)
Signed change orders not billed ($)
Free to use and share. No warranty; general information, not tax, accounting or legal advice. Your bookkeeper or accountant keeps the official books.

## Budget
Job / address | Cost code | Description | Type (Sub / Material / Labor / Other) | Original budget $ | Signed change orders $ | Revised budget $ | Actual to date $ | Variance $ (+ under / - over) | Variance % | Share of budget used | Work done? (Y/N) | Flag | Notes

## Costs
Date | Job / address | Cost code | Vendor / sub / employee | Bill / receipt # | Amount $ | Type (Bill / Receipt / Labor / Credit) | Paid (date) | Flag | Notes

## Change Orders
Job / address | CO # | Cost code | Description | Amount $ | Client signed (date) | Work done? (Y/N) | Billed (date or inv #) | Flag | Notes

## Settings
Settings
Warn when actual cost reaches this share of the revised budget (work not done) | 90%
Edit the value in column B (0.9 = 90%). It is your own warning level, not an industry figure.