## Start Here
TapeAndFloat Permit & Inspection Log (free)
For small remodelers, builders and GCs. One row per permit per job, one row per inspection, and flags for the deadlines that slip.
1. Permits sheet: one row per permit per job. Job / address, permit type (e.g. Building, Electrical, Plumbing, Mechanical), permit number,
applied, issued and expiration dates, whether the permit card is posted, work complete, final passed, final / CO closeout date, fees and who is responsible.
Copy the expiration date from the permit itself. Your local permit office sets its own rules for expiration, extensions and closeout.
2. Inspections sheet: one row per required inspection. Job, permit number (same as on Permits), inspection name, the date you need it,
requested (Y/N) and when, the inspection date, result (Pass, Fail, Partial) and any re-inspection date. Request by is worked out from Settings.
3. Settings: how many days before expiration to warn you, your inspection request lead time, and how long to wait on an application before flagging it.
Red = expired, expiring soon, failed or partial with no re-inspection, or work done but final not passed.
Yellow = no permit number, card not posted, fees unpaid, not issued yet, inspection not requested by your lead time, or a result missing. Green = final passed.
Tip: review both sheets at the same time each week, and close out each permit (final passed, closeout date logged) before you move on from the job.
Guide: https://gc.tapeandfloat.com/guides/permit-inspection-tracking-remodelers.html
Want this kept up for you? During the TapeAndFloat pilot we set it up one piece at a time from the permit emails and texts you forward,
in your own Google Sheet, with deadline flags: permit expiring, inspection not requested, failed with no re-inspection, final not closed.
You approve before anything goes out, and a real person reviews everything.
Free 60-day pilot: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Summary (updates automatically)
Open permits (final not passed)
Permits expired
Permits expiring soon
Permits with no permit number
Work done but final not passed
Permits with fees unpaid
Inspections not requested by your lead time
Failed or partial inspections with no re-inspection date
Permit rows with any flag
Inspection rows with any flag
Free to use and share. No warranty; general information, not legal or code advice. Your local permit office sets its own rules.

## Permits
Job / address | Permit type | Permit number | Applied (date) | Issued (date) | Expires (date) | Card posted? (Y/N) | Work complete? (Y/N) | Final passed? (Y/N) | Final / CO closeout (date) | Fees owed ($) | Fees paid? (Y/N) | Responsible | Days to expiry | Flag | Notes

## Inspections
Job / address | Permit number | Inspection (e.g. Rough plumbing) | Needed by (date) | Requested? (Y/N) | Requested on (date) | Inspection date | Result | Re-inspection date | Responsible | Request by (date) | Flag | Notes

## Settings
Settings
Warn this many days before a permit expires | 30
Request inspections this many days before you need them (use your office's lead time) | 2
Flag an application not issued after this many days | 14
Edit the values in column B. These are your own settings, not a code or permit-office rule.