## Start Here
TapeAndFloat Pre-Start Checklist (free)
For small home builders, remodelers and GCs. The handoff from signed contract to first day on site, one row per job per item:
deposit, contract, permits, selections, materials and lead times, schedule, sub confirmations, COIs and W-9s, site access and utilities, and the client kickoff note.
1. Jobs sheet: one row per job with the client, address and planned start date. The Checklist reads the start date from here.
2. Checklist sheet: one row per job per item. Pick the item from the list (edit the list on Settings), then fill in the owner (one person),
the due date, the status, the done date and a proof link (signed contract, deposit receipt, permit, sub's written confirmation, COI file, photo).
Start date and days to start fill in automatically. Use Not needed for items that don't apply to the job.
3. Settings: the standard item list with how many days before start each one should be done, and how many days before start an open item is flagged.
The numbers there are EXAMPLES, not rules. Deposit terms are set by your contract; which permits you need and when work can start are set by your
city or county permit office. Check them or ask an attorney.
Red = an item still open on or past the job's start date, or due after the start date.
Yellow = no owner, no due date, overdue, done with no proof link, done with no done date, start coming up with the item still open, or job not on the Jobs sheet.
Green = complete row.
4. The first rows are EXAMPLES (the job name starts with EXAMPLE). Delete them, on Jobs and Checklist, before you start.
Tip: copy the Settings item list into the Checklist for every new job the day the contract is signed, so nothing depends on memory.
General information only, not legal advice.
Guide: https://gc.tapeandfloat.com/guides/contract-to-start-handoff-checklist.html
Want help keeping it up? During the TapeAndFloat pilot, checklist items still open past the start date get flagged, and it drafts the follow-up
for you to approve. Nothing is sent on its own, and during the pilot a real person reviews everything.
Free 60-day pilot: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Summary (updates automatically)
Jobs listed
Checklist rows
Open items
Done or not needed
Open past the start date
No owner
No due date
Due after the start date
Overdue (open, due date passed)
Done with no proof link
Done with no done date
Start coming up, item still open
Job not on the Jobs sheet
Rows with any flag
Free to use and share. No warranty; general information only, not legal advice.

## Checklist
Job | Item | Owner (one person) | Due date | Status | Done date | Proof link (contract, receipt, permit, confirmation, COI) | Notes | Start date (from Jobs) | Days to start | Flag
EXAMPLE Smith kitchen (delete this row) | Contract signed by both sides | Owner | 2026-09-26 | Done | 2026-09-25 | https://drive.example.com/smith/contract.pdf | Example: complete row
EXAMPLE Smith kitchen (delete this row) | Deposit received (per your contract) | Office | 2026-10-06 | Done | 2026-10-07 | https://drive.example.com/smith/deposit.pdf | Example: complete row
EXAMPLE Smith kitchen (delete this row) | Permits issued | Owner | 2026-10-22 | In progress |  |  | Example: permit still not issued and the job started (red)
EXAMPLE Smith kitchen (delete this row) | Subs confirmed in writing with dates | PM | 2026-10-20 | Done | 2026-10-20 |  | Example: done but no proof link
EXAMPLE Smith kitchen (delete this row) | COIs and W-9s on file for every sub |  | 2026-10-21 | Open |  |  | Example: no owner, open past start
EXAMPLE Smith kitchen (delete this row) | Client kickoff note sent (start date, contacts, what to expect) | Office | 2026-10-23 | Not needed |  |  | Example: not needed (client met on site)
EXAMPLE Lee addition (delete this row) | Permits applied for | Owner | 2026-10-25 | Done | 2026-10-24 | https://drive.example.com/lee/permit-app.pdf | Example: complete row
EXAMPLE Lee addition (delete this row) | Selections finalized (client sign-off) | PM |  | Open |  |  | Example: no due date, start coming up
EXAMPLE Lee addition (delete this row) | Materials ordered / long lead times confirmed | Office | 2026-11-10 | Open |  |  | Example: due after the start date (red)
EXAMPLE Lee addition (delete this row) | Subs confirmed in writing with dates | PM | 2026-10-29 | In progress |  |  | Example: start coming up, still open
EXAMPLE Lee addition (delete this row) | Site access, utilities, dumpster and toilet arranged | PM | 2026-10-23 | Done |  | https://drive.example.com/lee/site.jpg | Example: done with no done date
Formulas:
Days to start = IF(N([Start date (from Jobs)])=0,"",N([Start date (from Jobs)])-TODAY())

## Jobs
Job | Client | Address | Planned start date | Status | Items | Open items | Open past start | Rows with a flag | Notes
EXAMPLE Smith kitchen (delete this row) | Smith | Oak St | 2026-10-24 | Started
EXAMPLE Lee addition (delete this row) | Lee | Pine Rd | 2026-11-01 | Not started

## Settings
Settings
Flag an open item when the job starts within this many days (EXAMPLE value) | 7
Item (edit the list; the Checklist item dropdown reads it) | Done this many days before start (EXAMPLE)
Contract signed by both sides | 21
Deposit received (per your contract) | 14
Permits applied for | 21
Permits issued | 3
Selections finalized (client sign-off) | 14
Materials ordered / long lead times confirmed | 10
Schedule set (start date + first 2 weeks) | 7
Subs confirmed in writing with dates | 5
COIs and W-9s on file for every sub | 3
Site access, utilities, dumpster and toilet arranged | 3
Client kickoff note sent (start date, contacts, what to expect) | 2
Edit the yellow cells. These are your own settings, not rules. Deposit terms are set by your contract; permits by your city or county permit office. Check them or ask an attorney.