## Start Here
TapeAndFloat Punch List & Warranty Callback Tracker (free)
For small home builders, GCs and remodelers. One row per item: punch items at the end of a job and warranty callbacks after move-in can share this log.
1. The day an item comes in (walkthrough, text, photo, voicemail, email): job, what's wrong in plain words, room or area, type, date reported, who reported it.
2. Assign it: the trade or sub responsible and their phone or email. Send each sub ONE message with all of their items for that job.
3. Due date fills in automatically: reported date + the days on the Settings sheet (punch and warranty set separately, edit them to match
your own contract or warranty document). Type your own date in 'Due date override' for any item.
4. Close with proof: enter the completed date, then Y when the homeowner signed off and Y when before/after photos are saved.
5. Back-charges: if your sub agreement allows charging a sub for work you had to finish, enter the amount and the date or invoice # you billed it.
Red = past due. Yellow = due within the 'due soon' days, no sub assigned, done without homeowner sign-off or photos, or back-charge not billed.
Green = done, signed off, photos saved, nothing left to bill.
Tip: review the open items every week. Past due = call the sub, not another text.
Guide: https://gc.tapeandfloat.com/guides/punch-list-warranty-callbacks.html
Want this kept up for you? TapeAndFloat reads the texts, photos and voicemails you forward, adds the rows to your own Google Sheet,
drafts each sub's item list for you to approve, and lists past-due and unconfirmed items every morning.
Free 60-day pilot, no card: https://gc.tapeandfloat.com/#pilot Questions: james@tapeandfloat.com
Summary (updates automatically)
Open items
Past due
Due soon
No sub assigned
Done without homeowner sign-off
Done without photos
Back-charges not billed (count)
Back-charges not billed ($)
Free to use and share. No warranty; general information, not legal advice. Follow your own contract, warranty document and sub agreements.

## Items
Job / address | Item (what's wrong) | Location / room | Type (Punch / Warranty) | Reported (date) | Reported by | Responsible trade / sub | Sub phone / email | Due date override | Due date | Days left | Status | Completed (date) | Homeowner sign-off? (Y/N) | Before/after photos? (Y/N) | Back-charge to sub $ | Back-charge billed (date or inv #) | Flag | Notes

## Settings
Settings
Default days to fix a PUNCH item (after reported date) | 7
Default days to fix a WARRANTY callback (after reported date) | 14
'Due soon' warning (days before due date) | 3
Edit the numbers in column B. Use the response times your own contract or warranty document promises.